## 00_Dashboard
AI-Native IT Service Management Platform — Product & Delivery Plan
Independent product specification benchmarked against modern ITSM capabilities; designed for dev, QA, security, product, and architecture teams.
Product Principle | Definition | Plan Metric | Value
Product Type | AI-native, ITIL-aligned ITSM platform; API-first; workflow-driven; multi-tenant; deployable as SaaS, private cloud, or customer-hosted. | Total features | 135
Primary Goal | Unify IT incidents, problems, changes, requests, knowledge, service configuration, SLAs, and support operations in one governed system. | P0 features | 79
AI Goal | Use explainable, permission-aware AI agents to triage, recommend, execute approved actions, and automate routine support work. | MVP features | 41
Differentiation | Composable architecture, faster implementation, open integrations, customer-controlled data/model choices, governed agent execution, and optional GMH integration. | V1 features | 57
Initial Boundary | Core ITSM is native. Deep monitoring/AIOps, endpoint management, advanced SAM/HAM, and security operations are integrations or later modules. | AI / Agentic features | 20
Success Definition | Production-grade service management with measurable MTTR reduction, higher self-service deflection, safer changes, auditability, and extensibility. | Security / GRC requirements | 27
|  | NFR / SLO requirements | 24
|  | Release | Scope Intent | Core Modules | AI Level | Enterprise Readiness | Exit Gate | Target State
|  | MVP | Operational service desk foundation | Incident, request, catalog, knowledge, SLA, core RBAC, basic CMDB | Assistive AI | SSO + audit + backups | Core workflows pass UAT | Pilot-ready
|  | V1 | Full ITSM suite | Problem, change, major incident, on-call, service graph, advanced workspace | Copilot + recommendations | Multi-region controls + advanced RBAC | Security and performance gates | Production-ready
|  | V1.5 | Automation and enterprise scale | Workflow builder, integrations, advanced analytics, import/migration | Bounded autonomous actions | Policy engine + stronger isolation | Automation safety evaluation | Scale-ready
|  | V2 | Autonomous service operations | Event/AIOps connectors, proactive remediation, expanded asset/service operations | Multi-agent orchestration | AI governance + model routing | Autonomy risk gates | Autonomous-ready
|  | Later | Enterprise service management extensions | HR/procurement/facilities templates; marketplace | Cross-domain agents | Marketplace governance | Domain certification | Platform expansion

## 01_Product_Vision
Product Vision, Objectives & Scope
Product definition for architecture and delivery decisions.
ID | Category | Statement | Why It Matters | Measure / KPI | Release | Owner | Notes
OBJ-001 | Objective | Create a single operational system for IT support and service delivery. | Eliminates fragmented ticketing and inconsistent process execution. | % IT workflows managed on platform | MVP | Product
OBJ-002 | Objective | Implement ITIL-aligned incident, problem, change, request, knowledge, and service configuration practices. | Meets procurement expectations and reduces process redesign. | Core practice UAT pass rate | V1 | Product + Architecture
OBJ-003 | Objective | Make self-service the default entry point for standard support and service requests. | Reduces service desk volume and improves employee experience. | Self-service deflection rate | MVP | Product
OBJ-004 | Objective | Give service teams one unified workspace with context, relationships, SLAs, collaboration, and recommended next actions. | Reduces swivel-chair work and MTTR. | Median handling time / MTTR | V1 | UX + Product
OBJ-005 | Objective | Make service and configuration context first-class through a CMDB/service graph. | Enables impact analysis for incidents, problems, and changes. | CI coverage, completeness, relationship quality | V1 | Platform
OBJ-006 | Objective | Provide governed AI agents that can assist and, where explicitly permitted, execute bounded actions. | Differentiates product while preserving human control and auditability. | AI task success rate; override rate; autonomous action error rate | V1.5 | AI + Security
OBJ-007 | Objective | Support SaaS, private-cloud, and customer-hosted deployment patterns. | Required for regulated and data-sovereignty buyers. | Deployment modes certified | V1.5 | Platform
OBJ-008 | Objective | Expose all core business capabilities through versioned APIs and events. | Prevents lock-in and enables ecosystem integration. | API coverage and webhook/event coverage | V1 | Platform
GOAL-001 | Business Goal | Reduce mean time to acknowledge and resolve incidents. | Direct customer value. | MTTA, MTTR | V1 | Product
GOAL-002 | Business Goal | Reduce repeat incidents through problem and known-error workflows. | Improves reliability and lowers support cost. | Repeat incident rate | V1 | Product
GOAL-003 | Business Goal | Increase successful, low-risk change throughput. | Supports DevOps without losing governance. | Change success rate; failed change rate | V1 | Product
GOAL-004 | Business Goal | Automate repetitive requests such as access, password, software, distribution list, and standard provisioning. | Supports zero-touch fulfillment where safe. | Automation rate; fulfillment time | V1.5 | Automation
GOAL-005 | Business Goal | Give leaders transparent service performance and experience metrics. | Enables continual service improvement. | SLA compliance; CSAT; backlog age; FCR | V1 | Analytics
PRIN-001 | Design Principle | API-first and event-driven; UI is a client of the same business APIs. | Keeps architecture composable and testable. | % UI mutations using public/internal service APIs | MVP | Architecture
PRIN-002 | Design Principle | Policy before autonomy: AI cannot bypass RBAC, approval, segregation-of-duties, or change controls. | Prevents AI from becoming a privileged side channel. | 0 unauthorized AI executions | MVP | AI + Security
PRIN-003 | Design Principle | Every automated decision must be attributable, explainable, and auditable. | Required for trust and regulated adoption. | Decision trace completeness | MVP | AI + Security
PRIN-004 | Design Principle | Configuration over customization for workflows, forms, SLAs, routing, notifications, and catalog items. | Reduces implementation cost and upgrade risk. | % customer needs met by config | V1 | Platform
PRIN-005 | Design Principle | Tenant isolation is enforced at identity, API, application, cache, queue, search, and storage layers. | Multi-tenant security cannot rely only on UI filtering. | Isolation test pass rate | MVP | Security
SCOPE-001 | In Scope | Incident, major incident, problem, change, request, catalog, knowledge, SLA/OLA, CMDB/service graph, on-call, workspace, portal, analytics, integration, audit, AI. | Defines core product. | Feature completion | V1.5 | Product
SCOPE-002 | Later / Integration | Full endpoint management, network discovery, deep AIOps event correlation, vulnerability response, advanced SAM/HAM, SecOps. | Avoids over-expanding core release. | Integration coverage | V2+ | Product
SCOPE-003 | Optional Product Integration | GMH can provide governed long-term agent memory/context; ITSM must remain independently deployable. | Allows portfolio synergy without hard dependency. | ITSM works with GMH on/off | V1.5 | Architecture

## 02_Feature_Backlog
Detailed Feature Backlog
Prioritized capabilities. Release indicates earliest planned product increment; status is initialized as Planned.
Feature ID | Domain | Epic | Feature / Capability | Detailed Requirement | Primary Personas | Dependencies | Priority | Release | Complexity | Acceptance / Done Condition | Status | Source / Benchmark
PLT-001 | Platform Foundation | Tenant | Multi-tenant organization model | Organizations, business units, departments, locations, cost centers, groups and tenant hierarchy; support single-tenant mode. | Platform Admin | Identity/data model | P0 | MVP | L | Tenant-scoped data is isolated; org hierarchy queries work. | Planned | Internal product requirement
PLT-002 | Platform Foundation | Identity | SAML/OIDC SSO | Enterprise SSO, IdP metadata, domain discovery, JIT provisioning, session controls. | Admin/Security | Identity provider | P0 | MVP | L | Configured IdP authenticates users and tenant session policy is enforced. | Planned | Internal product requirement
PLT-003 | Platform Foundation | Identity | SCIM 2.0 provisioning | Provision/deprovision users and groups; map memberships and role assignments. | Admin/Security | Identity | P1 | V1 | M | SCIM create/update/deactivate/group sync passes interoperability tests. | Planned | Internal product requirement
PLT-004 | Platform Foundation | Authorization | RBAC + scoped permissions | Role, group, object, record, field and action permissions with default deny and least privilege. | Admin/Security | Identity/policy | P0 | MVP | XL | Unauthorized API/UI access is blocked and audited. | Planned | Internal product requirement
PLT-005 | Platform Foundation | Authorization | Delegated administration | Domain/business-unit admins can manage only explicitly delegated scope. | Tenant Admin | RBAC | P1 | V1 | M | Delegated admin cannot read/mutate outside assigned domain. | Planned | Internal product requirement
PLT-006 | Platform Foundation | Forms | Metadata-driven form engine | Configurable fields, sections, conditional visibility, mandatory rules, references, computed fields. | Admin/Agent | Schema service | P0 | MVP | XL | Admin changes form without code; UI/API validation stays consistent. | Planned | Internal product requirement
PLT-007 | Platform Foundation | Records | Human-readable numbering | Configurable prefixes and unique sequences for INC/PRB/CHG/REQ/RITM/TASK/KB/CI. | Agent/Admin | Database | P1 | MVP | S | Numbers are unique, immutable, searchable. | Planned | Internal product requirement
PLT-008 | Platform Foundation | Attachments | Secure attachments | Malware scanning hook, file type/size policy, encryption, signed access, retention, safe preview. | All | Object storage/AV | P0 | MVP | L | Disallowed files are rejected; access is scoped and audited. | Planned | Internal product requirement
PLT-009 | Platform Foundation | Activity | Journal and activity stream | Internal work notes, public comments, state/field history, system actions, mentions and watchers. | Agent/Requester | Notifications | P0 | MVP | M | Actor/time/visibility/history retained; internal notes cannot leak. | Planned | Internal product requirement
PLT-010 | Platform Foundation | Search | Global search | Cross-record ACL-aware search with facets, recency, synonyms and semantic option. | All | Search index | P1 | V1 | L | Search returns only authorized records within latency target. | Planned | Internal product requirement
PLT-011 | Platform Foundation | Localization | Locale/timezone/language framework | Per-user timezone/locale, translated labels, date/number formats, content language tags. | All | UI framework | P2 | V1.5 | M | Same record renders correctly across timezones/locales. | Planned | Internal product requirement
PLT-012 | Platform Foundation | Configuration | Feature flags and tenant settings | Staged rollout, tenant-specific enablement and environment configuration. | Admin/DevOps | Config service | P0 | MVP | M | Feature toggles without deployment and is audited. | Planned | Internal product requirement
PLT-013 | Platform Foundation | Audit | Immutable audit trail | Create/update/delete/auth/permission/admin/integration/AI/action events with tamper-resistant retention/export. | Security/Auditor | Audit store | P0 | MVP | L | Privileged actions emit immutable actor/target/correlation evidence. | Planned | Internal product requirement
PLT-014 | Platform Foundation | Retention | Retention/legal hold/purge | Per-record retention, legal hold, soft delete and reconciled purge from derived stores. | Security/Admin | Storage lifecycle | P1 | V1 | L | Legal hold blocks purge; completed purge is verifiable. | Planned | Internal product requirement
INC-001 | Incident Management | Intake | Multi-channel incident creation | Portal, agent UI, email, API, chat and monitoring connector normalize into one incident schema. | Requester/Agent | Email/API | P0 | MVP | L | Source is retained and all channels create same canonical record. | Planned | https://www.servicenow.com/in/products/incident-management.html
INC-002 | Incident Management | Triage | Impact × urgency priority matrix | Configurable priority matrix with controlled override/reason and recalculation rules. | Agent | Rules engine | P0 | MVP | M | Priority is deterministic; overrides are audited. | Planned | Internal product requirement
INC-003 | Incident Management | Triage | Category/service/CI classification | Hierarchical taxonomy, dependent choices, service/CI association and learned suggestions. | Agent | CMDB/AI | P0 | MVP | L | Valid taxonomy dependencies and CI/service references are enforced. | Planned | Internal product requirement
INC-004 | Incident Management | Routing | Assignment rules and queues | Route by service, CI, category, location, VIP, schedule, load, skill and escalation. | Agent/Manager | Rules/on-call | P0 | MVP | XL | Routing selects valid queue/owner with trace. | Planned | Internal product requirement
INC-005 | Incident Management | Lifecycle | Incident state model | New, assigned, in progress, pending, resolved, closed, canceled with configurable guarded transitions. | Agent | Workflow | P0 | MVP | M | Invalid transitions blocked in UI and API. | Planned | Internal product requirement
INC-006 | Incident Management | Resolution | Resolution validation | Structured resolution code/notes, workaround/KB link, reopen policy and evidence rules. | Agent | Knowledge | P0 | MVP | S | Cannot resolve without configured mandatory evidence. | Planned | Internal product requirement
INC-007 | Incident Management | Collaboration | Swarming/collaboration | Mentions, resolver swarm, watchers, linked chat/bridge, handoff notes and collaboration timeline. | Agent | Notifications | P1 | V1 | M | Collaboration does not change ownership unless policy says so. | Planned | Internal product requirement
INC-008 | Incident Management | Linking | Parent/child/duplicate incidents | Link duplicates and related incidents/problems/changes; configurable parent cascades. | Agent | Relationships | P1 | V1 | M | Relationships are bidirectional and auditable. | Planned | Internal product requirement
INC-009 | Incident Management | Knowledge | Similar incidents/knowledge suggestions | Surface authorized KB, known errors, recent similar incidents and service history. | Agent | Search/AI | P1 | V1 | L | Recommendations cite authorized evidence. | Planned | Internal product requirement
INC-010 | Incident Management | SLA | Incident SLA timers | Response/assignment/restore/resolution timers, pause rules, business calendars and breach warnings. | Agent/Manager | SLA engine | P0 | MVP | XL | Timer math passes timezone/holiday/pause tests. | Planned | Internal product requirement
INC-011 | Incident Management | Reopen | Requester reopen policy | Reopen within allowed window, preserve resolution and track reopen rate/reason. | Requester/Agent | Lifecycle | P1 | MVP | S | Reopen is auditable and SLA behavior follows policy. | Planned | Internal product requirement
MIM-001 | Major Incident | Declaration | Major incident candidate/declaration | Promote candidate; capture impact, affected services, commander and comms lead. | Incident Commander | Incident/CMDB | P0 | V1 | L | Declaration initializes major incident coordination workspace. | Planned | Internal product requirement
MIM-002 | Major Incident | Coordination | War-room workspace | Timeline, tasks, stakeholders, services, bridge/chat links, decisions, updates and recovery checkpoints. | Incident Commander/Resolver | Collaboration | P0 | V1 | XL | Critical coordination context is available in one workspace. | Planned | Internal product requirement
MIM-003 | Major Incident | Communications | Stakeholder communication plans | Audience templates, cadence, approval, email/SMS/chat/status-page connectors and delivery status. | Comms Lead | Notifications | P0 | V1 | L | Each communication records audience/channel/approver/time/status. | Planned | Internal product requirement
MIM-004 | Major Incident | PIR | Post-incident review | Timeline, impact, cause, lessons, actions, owners/dates; AI draft with evidence links. | Problem Manager | Problem/AI | P1 | V1.5 | L | PIR sources are traceable and actions track to closure. | Planned | Internal product requirement
PRB-001 | Problem Management | Intake | Create problem from incidents/analysis | Manual, incident cluster, major incident, analytics signal or API. | Problem Manager | Incident | P0 | V1 | M | Problem retains source relationships and rationale. | Planned | https://www.servicenow.com/products/problem-management.html
PRB-002 | Problem Management | Lifecycle | Problem lifecycle/tasks | Assess, RCA, fix in progress, resolved, closed with task orchestration. | Problem Manager | Workflow | P0 | V1 | M | Transitions enforce RCA/fix evidence. | Planned | Internal product requirement
PRB-003 | Problem Management | RCA | Root cause analysis workspace | 5 Whys/fishbone fields, evidence, hypotheses, timeline, validation and CI/service links. | Problem Manager/Resolver | CMDB | P0 | V1 | L | RCA method and evidence are reviewable. | Planned | Internal product requirement
PRB-004 | Problem Management | Known Error | Known error database | Symptoms, affected services/CIs, workaround, fix status and review/expiry. | Agent/Problem Manager | Knowledge | P0 | V1 | M | Known errors are searchable from incident triage. | Planned | Internal product requirement
PRB-005 | Problem Management | Analytics | Incident clustering/trends | Link incident frequency, time distribution, service impact and repeat patterns. | Problem Manager | Analytics | P1 | V1 | L | Problem view quantifies related incident trend. | Planned | Internal product requirement
PRB-006 | Problem Management | Remediation | Corrective/preventive actions | Create change/request/task from fix plan with owner/state/evidence/closure. | Problem Manager | Change/task | P0 | V1 | M | Remediation actions are traceable to problem. | Planned | Internal product requirement
PRB-007 | Problem Management | Proactive | Proactive problem candidates | Detect repeat/anomalous patterns and suggest problem creation with evidence/confidence. | Problem Manager | AI/analytics | P1 | V1.5 | L | No silent auto-creation unless policy explicitly allows. | Planned | Internal product requirement
CHG-001 | Change Management | Request | Normal/standard/emergency change record | Scope, affected services/CIs, implementation, test, rollback and validation plans. | Change Initiator | CMDB/workflow | P0 | V1 | L | Required data varies correctly by change model. | Planned | https://www.servicenow.com/products/change-management.html
CHG-002 | Change Management | Risk | Explainable risk scoring | CI criticality, outage, timing, past failure, blast radius, test evidence and conflicts. | Change Manager | CMDB/analytics | P0 | V1 | XL | Risk score is reproducible with factor trace. | Planned | Internal product requirement
CHG-003 | Change Management | Approvals | Dynamic approval policies | Risk/service/environment-based serial, parallel, quorum and delegated approvals. | Approver/Change Manager | Workflow/RBAC | P0 | V1 | L | Approval path is deterministic and SoD-aware. | Planned | Internal product requirement
CHG-004 | Change Management | Standard Change | Pre-authorized standard changes | Template library, eligibility conditions and constrained auto-approval. | Change Initiator | Workflow | P0 | V1 | M | Noncompliant standard change cannot use pre-authorization. | Planned | Internal product requirement
CHG-005 | Change Management | Emergency | Emergency change workflow | Accelerated approval, mandatory reason/evidence and after-the-fact review. | Change Manager | Workflow | P0 | V1 | M | Emergency path remains controlled/auditable. | Planned | Internal product requirement
CHG-006 | Change Management | Calendar | Change calendar | Service/CI/team/environment calendar, maintenance/blackout windows, freezes and overlays. | Change Manager/SRE | Calendar/CMDB | P0 | V1 | L | Conflicts/windows are visible before authorization. | Planned | Internal product requirement
CHG-007 | Change Management | Conflict | Conflict detection | Overlapping changes, shared dependencies, blackout violations, resource/on-call conflicts. | Change Manager | CMDB/service graph | P0 | V1 | XL | Engine returns affected records and reasons. | Planned | Internal product requirement
CHG-008 | Change Management | CAB | CAB workbench | Agenda, change filters, risk summary, attendees, recommendations/votes, notes and decisions. | CAB/Change Manager | Approvals | P1 | V1 | L | CAB result updates change with decision trace. | Planned | Internal product requirement
CHG-009 | Change Management | Implementation | Implementation task orchestration | Tasks, owners, prerequisites, checkpoints, evidence and completion gates. | Resolver | Workflow | P0 | V1 | M | Required tasks/checkpoints block premature completion. | Planned | Internal product requirement
CHG-010 | Change Management | Review | Post-implementation review | Success/failure, incidents caused, rollback, lessons and change-performance history. | Change Manager | Incident/analytics | P0 | V1 | M | Outcome feeds future risk scoring. | Planned | Internal product requirement
CHG-011 | Change Management | DevOps | CI/CD change integration | Pipeline APIs/webhooks auto-create/update evidence for deployments and approved changes. | Developer/SRE | Integration | P1 | V1.5 | XL | No shared human credentials; project identity is authenticated. | Planned | Internal product requirement
CHG-012 | Change Management | AI | AI change-plan draft | Draft implementation/test/rollback/validation plan from approved patterns; human review required. | Change Initiator | AI/knowledge | P1 | V1.5 | M | Draft cites sources and cannot approve itself. | Planned | Internal product requirement
REQ-001 | Request Management | Request | Request + request items | Order container with one/many items; each item has workflow, tasks, approvals and SLA. | Requester/Fulfiller | Catalog/workflow | P0 | MVP | L | REQ/RITM/task hierarchy is traceable. | Planned | https://www.servicenow.com/products/request-management.html
REQ-002 | Request Management | Catalog | Service catalog taxonomy | Categories, searchable items, eligibility, owner, cost metadata and audience. | Requester/Catalog Admin | Portal | P0 | MVP | L | Only eligible items are discoverable/orderable. | Planned | Internal product requirement
REQ-003 | Request Management | Catalog Builder | No-code catalog item builder | Variables, conditions, validations, workflow binding, versioning, preview/test/publish. | Catalog Admin | Forms/workflow | P0 | V1 | XL | Admin publishes new item without code after validation. | Planned | https://www.servicenow.com/products/it-service-automation-applications/service-catalog.html
REQ-004 | Request Management | Approvals | Request approval matrix | Manager, owner, cost center, data owner/security with serial/parallel/quorum patterns. | Approver | Workflow/org | P0 | MVP | L | Approval path uses current request context and is audited. | Planned | Internal product requirement
REQ-005 | Request Management | Fulfillment | Reusable fulfillment workflows | Human tasks, integrations, waits, validation and compensation/rollback. | Fulfiller/Admin | Workflow | P0 | V1 | XL | Reusable subflow can serve multiple catalog items. | Planned | Internal product requirement
REQ-006 | Request Management | Status | Requester-friendly status | Progress, blockers, next approver, timestamps and notifications without internal-only details. | Requester | Workflow | P0 | MVP | M | Displayed status matches workflow truth. | Planned | Internal product requirement
REQ-007 | Request Management | Cancellation | Cancel/withdraw/compensate | Policy-controlled cancellation with safe rollback/compensation for completed steps. | Requester/Fulfiller | Workflow | P1 | V1 | M | Irreversible completed actions are explicitly disclosed. | Planned | Internal product requirement
REQ-008 | Request Management | Bundles | Service bundles/kits | Bundle onboarding/offboarding/device/access requests into related child items. | Requester/Fulfiller | Catalog | P2 | V1.5 | M | Bundle shares context while retaining child lifecycle. | Planned | Internal product requirement
REQ-009 | Request Management | Eligibility | Catalog eligibility policy | Geography, employment, department, role, license, device and cost-center eligibility. | Requester | Policy | P1 | V1 | L | Crafted API request cannot bypass eligibility. | Planned | Internal product requirement
REQ-010 | Request Management | AI | Conversational catalog ordering | Chat gathers required fields, checks eligibility and summarizes before submit. | Requester | AI/catalog | P1 | V1.5 | L | AI never skips mandatory/approval controls. | Planned | Internal product requirement
KB-001 | Knowledge Management | Lifecycle | Article lifecycle | Draft, review, publish, expire, retire with owner, reviewers, audience, taxonomy and versioning. | Knowledge Author | Workflow | P0 | MVP | L | Only approved published version is requester-visible. | Planned | Internal product requirement
KB-002 | Knowledge Management | Authoring | Rich editor/templates | How-to, troubleshooting, known-error, FAQ/policy templates with safe rich content. | Knowledge Author | UI | P1 | MVP | M | Content safely renders and templates are reusable. | Planned | Internal product requirement
KB-003 | Knowledge Management | Search | Full-text + semantic search | Keyword/facets/synonyms/typo tolerance/semantic retrieval with ACL-aware ranking. | Requester/Agent | Search | P0 | MVP | L | Restricted article/snippet never leaks. | Planned | Internal product requirement
KB-004 | Knowledge Management | Quality | Feedback/usefulness | Helpful/not helpful, comments, use, deflection linkage and stale-content flags. | All | Analytics | P1 | V1 | M | Owner gets actionable quality metrics. | Planned | Internal product requirement
KB-005 | Knowledge Management | Governance | Review/expiry policy | Periodic review, orphan detection, owner reassignment and expiry alerts. | Knowledge Manager | Scheduler | P1 | V1 | M | Expired content is excluded from default answers. | Planned | Internal product requirement
KB-006 | Knowledge Management | AI | AI-assisted drafting | Draft article from resolved work with citations, tags and redaction; human publish gate. | Knowledge Author | AI | P1 | V1.5 | M | Generated content is traceable and requires review. | Planned | Internal product requirement
CMDB-001 | CMDB & Service Graph | CI Model | Extensible CI class model | Base CI plus service, app, server, VM, DB, network, cloud, endpoint and software component classes. | CMDB Admin | Schema | P0 | MVP | XL | Class inheritance and tenant extensions are supported. | Planned | https://www.servicenow.com/docs/r/servicenow-platform/configuration-management-database-cmdb/manage-cmdb.html
CMDB-002 | CMDB & Service Graph | Relationships | Typed CI relationships | Depends on/runs on/hosted on/connects to/owned by/supports/part of with direction rules. | CMDB Admin | Graph | P0 | V1 | XL | Upstream/downstream impact queries are supported. | Planned | Internal product requirement
CMDB-003 | CMDB & Service Graph | Reconciliation | Identification and reconciliation | Deterministic identity, source precedence, merge, duplicate detection and attribute ownership. | CMDB Admin | Import | P0 | V1 | XL | Multi-source CI updates reconcile without destructive overwrite. | Planned | Internal product requirement
CMDB-004 | CMDB & Service Graph | Health | CMDB health metrics | Completeness, correctness, compliance, staleness, duplicates and orphan relationships. | CMDB Admin | Analytics | P1 | V1 | L | Health score drills to failing CIs. | Planned | Internal product requirement
CMDB-005 | CMDB & Service Graph | Import | Bulk CI import | CSV/JSON/API mapping, transform, dry-run, error queue, source attribution and reconciliation. | CMDB Admin | Import engine | P0 | MVP | L | Dry run shows insert/update/conflict before commit. | Planned | Internal product requirement
CMDB-006 | CMDB & Service Graph | Connectors | Connector framework | Scheduled connectors for cloud, endpoint, directory, monitoring and asset sources. | Integration Admin | Integration framework | P1 | V1.5 | XL | Checkpoint/retry/idempotency/source attribution work. | Planned | Internal product requirement
CMDB-007 | CMDB & Service Graph | Service Model | Business/technical service model | Service offerings, owners, consumers, criticality, support groups, dependencies and hours. | Service Owner | CMDB | P0 | V1 | L | Incidents/changes calculate affected service context. | Planned | Internal product requirement
CMDB-008 | CMDB & Service Graph | Impact | Impact analysis API | Return upstream services likely impacted by CI/service issue or change with explainable graph path. | Agent/Change Manager | Graph | P0 | V1 | L | Bounded graph path respects ACL and tenant. | Planned | Internal product requirement
CMDB-009 | CMDB & Service Graph | Visualization | Service dependency map | Interactive relationship graph with depth/filter limits and incident/change overlays. | Service Owner/Agent | Graph query | P1 | V1.5 | L | Map is responsive and graph traversal is bounded. | Planned | Internal product requirement
SLA-001 | SLA & Commitments | Definition | Configurable SLA/OLA/UC | Conditions, targets, calendars, pause/resume/stop rules and retroactive policy. | Service Manager | Scheduler | P0 | MVP | XL | Timer engine passes deterministic boundary tests. | Planned | Internal product requirement
SLA-002 | SLA & Commitments | Calendars | Business calendars/holidays | Tenant calendars, timezones, holidays, exceptions, 24×7/follow-the-sun. | Admin | Scheduler | P0 | MVP | L | Business elapsed time handles DST/holidays. | Planned | Internal product requirement
SLA-003 | SLA & Commitments | Escalation | Breach prediction/escalation | Threshold warnings, manager/on-call escalation and optional reassignment. | Agent/Manager | Notifications | P1 | V1 | M | Warning/breach fires once with timer trace. | Planned | Internal product requirement
WKS-001 | Agent Workspace | Queues | My work/team queues | Saved filters, SLA risk, priority, assignment, service, skill and aging. | Agent | Search | P0 | MVP | L | Queue results are ACL-aware. | Planned | Internal product requirement
WKS-002 | Agent Workspace | Record | Unified case workspace | Form, activity, CIs/services, SLAs, tasks, approvals, KB, similar records and requester context. | Agent | Core modules | P0 | V1 | XL | Core context is available without multiple screens. | Planned | https://www.servicenow.com/products/service-operations-workspace.html
WKS-003 | Agent Workspace | Productivity | Templates/macros/quick actions | Response templates and safe multi-step quick actions: child/problem/change/KB/task. | Agent | Rules | P1 | V1 | M | Quick actions are transactional and audited. | Planned | Internal product requirement
WKS-004 | Agent Workspace | AI | Agent copilot panel | Summarize, explain SLA, suggest next step, draft reply, retrieve knowledge and handoff summary. | Agent | AI/search | P0 | V1 | L | Outputs cite evidence and respect field ACL. | Planned | Internal product requirement
SSP-001 | Self-Service | Portal | Responsive employee portal | Search, help, request, ticket status, approvals, announcements/outages and favorites. | Requester | Portal | P0 | MVP | XL | Desktop/mobile web and keyboard accessibility pass. | Planned | Internal product requirement
SSP-002 | Self-Service | Profile | My incidents/requests | Unified history, filters, status, comments, attachments, reopen/cancel where allowed. | Requester | Core modules | P0 | MVP | M | Only own/delegated records visible. | Planned | Internal product requirement
SSP-003 | Self-Service | Approvals | My approvals | Approve/reject/delegate with context and step-up authentication for high risk. | Approver | Workflow | P0 | MVP | M | Decision captures actor/context/time. | Planned | Internal product requirement
SSP-004 | Self-Service | Chat | Conversational support | Knowledge Q&A, ticket/status, catalog ordering and human handoff with summary. | Requester | AI/chat | P1 | V1.5 | XL | Permissions persist across chat/handoff. | Planned | Internal product requirement
SSP-005 | Self-Service | Status | Service status/outage page | Approved planned maintenance, major incident/outage information and subscriptions. | Requester | MIM/CMDB | P1 | V1 | L | Only approved status content is published. | Planned | Internal product requirement
SSP-006 | Self-Service | Accessibility | WCAG-aligned UI | Keyboard, semantic labels, focus, contrast, reduced motion and screen-reader support. | All | Design system | P0 | MVP | L | Core journeys pass automated/manual accessibility gate. | Planned | Internal product requirement
AUT-001 | Workflow & Automation | Engine | Durable workflow engine | Stateful workflows with humans, timers, waits, retries, compensation, subflows, versions and correlation IDs. | Admin/Platform | Queue/DB | P0 | MVP | XXL | Workflow survives node restart and actions are idempotent. | Planned | Internal product requirement
AUT-002 | Workflow & Automation | Builder | Visual workflow builder | Triggers, conditions, actions, approvals, branches, subflows, testing, publish/version rollback. | Admin | Workflow | P0 | V1.5 | XXL | Non-developer builds/tests/publishes supported flow safely. | Planned | Internal product requirement
AUT-003 | Workflow & Automation | Rules | Business rule engine | Validation/defaults/assignment/actions with explicit order, trace and recursion guard. | Admin | Core platform | P0 | MVP | XL | Rules execute deterministically and are traceable. | Planned | Internal product requirement
AUT-004 | Workflow & Automation | Scheduler | Scheduled jobs | Cron/interval jobs, timezone, concurrency, missed-run policy and history. | Admin | Workers | P0 | MVP | L | Duplicate scheduled execution is prevented. | Planned | Internal product requirement
AUT-005 | Workflow & Automation | Actions | Reusable action library | HTTP/email/webhook/directory/cloud/record CRUD/approval/AI typed actions. | Admin/Developer | Integration | P1 | V1.5 | XL | Each action has typed schema and permission boundary. | Planned | Internal product requirement
AUT-006 | Workflow & Automation | Guardrails | Execution policy/dry run | Allow/deny by environment, tenant, risk and data class; preview side effects. | Security/Admin | Policy | P0 | V1.5 | L | High-risk actions cannot execute outside policy. | Planned | Internal product requirement
NTF-001 | Notifications | Email | Inbound/outbound email | Thread-safe ingestion, templates, correlation, bounce/retry and secure attachment behavior. | All | Mail provider | P0 | MVP | XL | Spoofed sender cannot gain privileged mutation. | Planned | Internal product requirement
NTF-002 | Notifications | Rules | Rule-driven multi-channel notifications | Email/SMS/chat/web notifications with throttling, digest, templates and localization. | All | Event bus | P0 | MVP | L | No duplicate notification storms; delivery trace exists. | Planned | Internal product requirement
NTF-003 | Notifications | Collaboration | Teams/Slack integration | Create/view/update tickets, approvals, support chat and notifications. | Requester/Agent | OAuth | P1 | V1.5 | XL | Workspace/tenant binding and least privilege scopes. | Planned | Internal product requirement
ONC-001 | On-Call Management | Schedule | On-call rotations | Primary/secondary, timezone, overrides, holidays and follow-the-sun schedules. | Manager/Resolver | Scheduler | P1 | V1 | XL | Current on-call resolves correctly at any time. | Planned | Internal product requirement
ONC-002 | On-Call Management | Escalation | Escalation policies | Sequential/parallel escalation, ack timeout, retries and channels. | Incident Commander | Notifications | P1 | V1 | L | Stops on acknowledgement and records timeline. | Planned | Internal product requirement
ONC-003 | On-Call Management | Handoff | Shift handoff summary | Open incidents/MIMs/risky changes/SLA risks with AI-assisted summary. | Resolver | Incident/change/AI | P2 | V1.5 | M | Summary cites source records and team scope. | Planned | Internal product requirement
ANA-001 | Analytics & Reporting | Dashboard | Role-based dashboards | Service desk, manager, change, problem, CMDB, service owner and executive dashboards. | Manager | Analytics | P0 | V1 | L | Permission-aware filters and drilldown. | Planned | Internal product requirement
ANA-002 | Analytics & Reporting | Metrics | Core KPI library | MTTA, MTTR, FCR, reopen, backlog age, SLA, CSAT, deflection, change success and repeat incidents. | Manager | Events | P0 | V1 | M | Metric definitions are documented/reproducible. | Planned | Internal product requirement
ANA-003 | Analytics & Reporting | Reporting | Ad hoc report builder | Saved datasets, filters, grouping, aggregation, charts and scheduled export. | Analyst | Query service | P1 | V1.5 | XL | Field security applies to report builder. | Planned | Internal product requirement
ANA-004 | Analytics & Reporting | Trend | Historical metric snapshots | Daily/weekly/monthly snapshots independent of mutable current state. | Manager | Analytics store | P1 | V1 | L | Historical metric doesn't change after later ticket edits. | Planned | Internal product requirement
ANA-005 | Analytics & Reporting | Experience | CSAT surveys | Post-resolution/fulfillment surveys, comments, sampling and opt-out. | Requester/Manager | Notifications | P1 | V1 | M | Secure survey results aggregate by allowed dimensions. | Planned | Internal product requirement
INT-001 | Integration Platform | API | REST API v1 | CRUD/query/action APIs, pagination, filtering, sparse fields, optimistic concurrency and OpenAPI. | Developer | API gateway | P0 | MVP | XL | Core UI mutations are API/service-backed and documented. | Planned | Internal product requirement
INT-002 | Integration Platform | Webhooks | Webhook subscriptions | Signed outbound events with retry/backoff/DLQ/replay/idempotency. | Developer | Event bus | P0 | V1 | L | Replay doesn't create duplicate side effects. | Planned | Internal product requirement
INT-003 | Integration Platform | Events | Internal domain event bus | Versioned record/SLA/workflow/notification/AI/security events. | Platform | Event bus | P0 | MVP | XL | At-least-once with idempotent consumers. | Planned | Internal product requirement
INT-004 | Integration Platform | Secrets | Vault integration | Credential references only; cloud vault/CyberArk/HashiCorp-style interfaces; never plaintext in logs/config. | Security/Admin | Vault | P0 | MVP | L | Secret cannot be retrieved through product after save. | Planned | Internal product requirement
INT-005 | Integration Platform | Directory | Entra ID/Google Workspace connectors | Users/groups plus approved actions under least-privilege OAuth/service principals. | Admin | OAuth/vault | P1 | V1.5 | XL | Scopes and each action are audited. | Planned | Internal product requirement
INT-006 | Integration Platform | Monitoring | Monitoring event intake | Normalized alert/event endpoint and mapping/correlation hooks. | SRE | Integration | P1 | V2 | L | Duplicate source events correlate by policy. | Planned | Internal product requirement
INT-007 | Integration Platform | DevOps | GitHub/GitLab/Azure DevOps/Jenkins connectors | PR/build/deploy/change evidence and incident links. | Developer/SRE | OAuth | P1 | V1.5 | XL | Signed events map to authenticated repo/project. | Planned | Internal product requirement
INT-008 | Integration Platform | Migration | Migration toolkit | Users/groups/incidents/requests/KB/CIs/attachments with mapping, dry run, checkpoint and reconciliation. | Implementation Team | Import | P1 | V1.5 | XL | Large import resumes and gives row-level report. | Planned | Internal product requirement
AI-001 | AI & Agentic | Foundation | Model gateway | Provider-neutral model registry/routing, tenant allowlist, cost/latency, redaction and retention controls. | AI Admin | LLM providers | P0 | V1 | XL | All LLM calls flow through gateway and can be disabled per tenant. | Planned | Internal product requirement
AI-002 | AI & Agentic | Retrieval | Permission-aware RAG | Retrieve KB/tickets/known errors/CI/service context with pre-retrieval ACL filtering and citations. | Agent/Requester | Search/vector | P0 | V1 | XL | Unauthorized documents cannot enter context/output. | Planned | Internal product requirement
AI-003 | AI & Agentic | Incident | Incident triage agent | Suggest classification/service/CI/assignment and related major incident/problem candidates with confidence/evidence. | Agent | Incident/CMDB | P0 | V1 | L | Human can override; evidence is shown. | Planned | https://www.servicenow.com/docs/r/it-service-management/now-assist-for-it-service-management-itsm/now-assist-itsm-ai-agents-use-cases.html
AI-004 | AI & Agentic | Incident | Investigation agent | Evidence-backed investigation plan, knowledge/history retrieval and permitted diagnostics. | Agent | RAG/tool gateway | P0 | V1.5 | XL | Conclusions cite evidence; side-effect tools require policy. | Planned | Internal product requirement
AI-005 | AI & Agentic | Incident | Bounded resolution agent | Execute approved low-risk runbooks with precheck/postcheck/rollback and human gate by risk. | Agent/Requester | Action gateway | P1 | V2 | XXL | Allowlisted action+scope only; complete audit. | Planned | Internal product requirement
AI-006 | AI & Agentic | Change | Change planning agent | Draft implementation/test/rollback plan and identify missing evidence. | Change Initiator | Change/RAG | P1 | V1.5 | L | Cannot approve; sources cited. | Planned | Internal product requirement
AI-007 | AI & Agentic | Change | Conflict assessor | Explain service graph, schedule and blackout conflicts alongside deterministic rule engine. | Change Manager | CMDB/calendar | P1 | V1.5 | XL | AI doesn't override authoritative conflict rules. | Planned | Internal product requirement
AI-008 | AI & Agentic | Problem | Problem/RCA assistant | Cluster repeat incidents, summarize symptoms and propose hypotheses/evidence collection. | Problem Manager | Analytics/RAG | P1 | V1.5 | XL | Does not assert root cause without evidence. | Planned | Internal product requirement
AI-009 | AI & Agentic | Knowledge | Knowledge generation agent | Draft KB/known-error/PIR from resolved work with citations and redaction. | Knowledge Author | RAG/redaction | P1 | V1.5 | L | No auto-publish. | Planned | Internal product requirement
AI-010 | AI & Agentic | Request | Request fulfillment agent | Gather missing fields and execute approved low-risk fulfillment under eligibility/approval policy. | Requester | Catalog/action gateway | P1 | V2 | XL | Cannot bypass eligibility/approval/SoD. | Planned | Internal product requirement
AI-011 | AI & Agentic | Workspace | Case summarization | Cited summaries for long timelines, escalation and handoffs. | Agent | LLM gateway | P0 | V1 | M | Private fields not exposed to unauthorized persona. | Planned | Internal product requirement
AI-012 | AI & Agentic | Communications | Draft requester response | Draft factual update from record + approved KB; no invented ETA. | Agent | LLM gateway | P1 | V1 | M | Unsupported claims are flagged/omitted. | Planned | Internal product requirement
AI-013 | AI & Agentic | Governance | AI policy engine | Use-case model/tool/data-class/autonomy/cost/steps/approval policy. | AI Admin/Security | Policy | P0 | V1.5 | XL | Policy evaluates before every model/tool invocation. | Planned | Internal product requirement
AI-014 | AI & Agentic | Governance | Agent execution trace | Persist task goal, evidence refs, tools, approvals, model/version, cost, outcomes and failures. | Security/Auditor | Audit | P0 | V1.5 | XL | Reviewer can reconstruct why action occurred. | Planned | Internal product requirement
AI-015 | AI & Agentic | Governance | Human-in-the-loop checkpoints | Dynamic approval/review by action risk, confidence, criticality and data sensitivity. | Agent/Approver | Workflow | P0 | V1.5 | L | Autonomy cannot exceed policy tier. | Planned | Internal product requirement
AI-016 | AI & Agentic | Evaluation | AI evaluation harness | Golden sets for task success, groundedness, leakage, tool correctness, regressions, cost and latency. | AI Team | Eval platform | P0 | V1 | XL | Release blocks on critical evaluation regression. | Planned | Internal product requirement
AI-017 | AI & Agentic | Memory | Governed memory boundary | Native short-lived case context; optional GMH adapter for governed cross-session memory. | AI Admin | GMH optional | P1 | V1.5 | L | ITSM works with GMH on/off; memory access is policy-scoped. | Planned | Internal product requirement
AI-018 | AI & Agentic | Multi-Agent | Agent handoff protocol | Typed envelope: task, evidence, permissions, constraints, unresolved questions, actions, provenance and expiry. | AI Team | Agent runtime | P1 | V2 | XL | Receiving agent cannot inherit privileges implicitly. | Planned | Internal product requirement
AI-019 | AI & Agentic | Safety | Prompt injection/tool abuse defenses | Untrusted-content labels, instruction hierarchy, tool validation, retrieval isolation and egress controls. | Security | AI gateway | P0 | V1 | XL | Adversarial tests show no privilege escalation. | Planned | Internal product requirement
AI-020 | AI & Agentic | Operations | AI usage analytics | Tokens/cost/latency/task success/fallback/override/blocked action/model mix by tenant/use case. | AI Admin | Analytics | P1 | V1.5 | M | Usage data is tenant-isolated. | Planned | Internal product requirement
ADM-001 | Administration | Console | Admin console | Tenant/org/roles/forms/taxonomy/workflows/SLAs/notifications/integrations/AI policy/flags. | Admin | Core platform | P0 | V1 | XL | Admin changes are versioned/audited. | Planned | Internal product requirement
ADM-002 | Administration | Config Transport | Configuration promotion | Signed config bundles dev→test→prod with diff/dependency check/rollback; excludes secrets. | Admin/Developer | Config store | P1 | V1.5 | XL | Promotion is deterministic and secret-free. | Planned | Internal product requirement
DEV-001 | Developer Platform | SDK | Typed API SDKs | Generated TypeScript/Python clients from OpenAPI with auth, pagination, retries, idempotency. | Developer | REST API | P2 | V1.5 | M | SDK contract tests match API. | Planned | Internal product requirement
DEV-002 | Developer Platform | Extensibility | Extension points | Webhooks, custom fields/tables namespace, UI slots, workflow actions and connector SDK. | Developer | Platform | P1 | V1.5 | XXL | Extensions cannot mutate core runtime/schema unsafely. | Planned | Internal product requirement

## 03_Workflows
Core Workflow Specifications
Reference lifecycle/state behavior for development and QA.
Workflow ID | Process | Step / State | Entry Criteria | Required Actions | Automation / AI | Approval / Control | Exit Criteria | Events Emitted | Failure / Exception
WF-INC-01 | Incident | New / Intake | Valid requester/source + minimum description | Normalize source, validate, classify basics, start SLA | AI triage optional | RBAC/input validation | Created and routed | incident.created | Quarantine malformed/unsafe input
WF-INC-02 | Incident | Assigned | Assignment resolved | Notify queue; establish ownership | Routing recommendation | Queue/skill policy | Accepted/auto-assigned | incident.assigned | Escalate if not acknowledged
WF-INC-03 | Incident | In Progress | Owner assigned | Investigate, communicate, update notes, create tasks | Investigation copilot | Tool actions policy-gated | Resolved or pending | incident.worked | Swarm/escalate/MIM candidate
WF-INC-04 | Incident | Pending | Awaiting requester/vendor/change/problem | Set reason and resume condition | Reminder automation | SLA pause policy | Condition satisfied | incident.pending | Auto-resume/escalate
WF-INC-05 | Incident | Resolved → Closed | Resolution evidence complete | Notify requester; reopen window | Resolution summary draft | Closure policy | Accepted/window expires | incident.resolved/closed | Reopen with reason
WF-MIM-01 | Major Incident | Candidate → Declared | High impact/correlation | Assess blast radius; assign commander/comms; start war room | AI impact summary | Authorized declaration role | Declared/rejected | major_incident.declared | Return to standard incident
WF-MIM-02 | Major Incident | Restore → PIR | Service restored | PIR, problem/action items, timeline/comms review | AI PIR draft | Human review | PIR approved/actions tracked | pir.created | Overdue action escalation
WF-PRB-01 | Problem | Assess → RCA | Problem created | Validate scope, link incidents, hypotheses/evidence | Clustering/RCA assist | Problem manager | Root cause/workaround evidence | problem.rca_completed | Continue investigation
WF-PRB-02 | Problem | Fix → Close | RCA validated | Create change/tasks; validate permanent fix | Suggested remediation | Change controls | Fix verified | problem.closed | Backout/new hypothesis
WF-CHG-01 | Change | Draft → Assess | Initiator authorized | Plan, risk, CIs/services, tests, rollback; conflict check | AI plan/conflict assist | RBAC/policy | Approval path calculated | change.assessed | Request more evidence
WF-CHG-02 | Change | Authorize → Schedule | Assessment complete | Approvals/CAB, reserve window, notify | AI explanation only | SoD/approval/freeze rules | Authorized/scheduled | change.authorized | Reject/expire/reassess
WF-CHG-03 | Change | Implement → Review | Window active | Execute tasks/checkpoints, capture evidence, validate outcome | Bounded runbooks optional | Execution policy | Success/failure recorded | change.closed | Rollback/incident/problem
WF-REQ-01 | Request | Submit → Approve | Eligible item + required vars | Create request/items; evaluate approvals | Conversational collection | Eligibility/SoD | Approved/rejected | request.submitted | Reject invalid/ineligible
WF-REQ-02 | Request | Fulfill → Close | Approved/no approval | Execute tasks/integrations, validate, compensate if needed | Bounded automation | Action policy | All items complete | request.fulfilled | Manual intervention/cancel
WF-KB-01 | Knowledge | Draft → Review → Publish | Author entitled | Author/review/version/audience/expiry | AI draft optional | Publisher gate | Published version | knowledge.published | Reject to draft
WF-AI-01 | Agentic Action | Plan → Authorize | Use case enabled | Build evidence-backed structured plan + requested tools | Agent planning | AI policy + RBAC + SoD | Approved action set | ai.action.authorized | Block/ask human
WF-AI-02 | Agentic Action | Execute → Verify | Authorized action set | Execute idempotently; postcheck; compensate/rollback | Agent runtime | Tool gateway/vault | Goal achieved/safe fail | ai.action.executed | Rollback/stop/escalate

## 04_Roles_Permissions
Roles & Permission Model
Role templates; atomic permissions/scopes remain authoritative.
Role | Purpose | Typical Read Scope | Create / Update | Approve | Administer | Sensitive Restrictions | Key Audit Events
Requester | Employee/end-user support | Own/delegated incidents/requests, published KB/status | Own comments/attachments; create incident/request | Only separate delegated approvals | No | No internal notes or other-user records | login, create/update, attachment, approval
IT Agent / Fulfiller | Resolve support work | Assigned/team queue + related service context | Incidents/tasks/work notes/requester updates | Normally no policy approvals | No | No security/role/AI policy changes | assignment/state/resolution/tool actions
Incident Manager | Coordinate incident process | Domain incidents/service context | Incident process fields/MIM candidate | Declare MIM if entitled | Limited incident config | Cannot bypass privileged controls | MIM declaration/escalation
Incident Commander | Lead major incident | MIM, affected services/CIs/stakeholders | MIM timeline/tasks/comms | Comms if policy grants | No | No security/admin change | MIM decisions/messages
Problem Manager | Own problem lifecycle | Problems/incidents/changes/KB/CIs | RCA/known errors/remediation | Problem closure if policy grants | Problem templates | Change SoD still applies | RCA/known-error publish/closure
Change Initiator | Submit changes | Own/team changes + relevant CI/service | Draft/update before lock points | No | No | Cannot alter risk/approval policy | change edits
Change Manager | Govern changes | Authorized-domain changes/impact | Assess/schedule/review | Per policy | Change models/CAB if delegated | SoD prevents inappropriate self-approval | risk override/approval/emergency
CAB Member | Review changes | CAB agenda/evidence | Comments/recommendation | Vote/recommend only | No | No unrelated records | CAB decision
Knowledge Author | Create knowledge | Permitted draft/published KB + source cases | Draft/update articles | No publish unless publisher | No | Cannot widen audience beyond entitlement | article edits
Knowledge Publisher | Govern knowledge | KB in domain | Review metadata | Publish/retire | Knowledge policy | Cannot expose restricted source facts | publish/retire/audience
CMDB Admin | Maintain configuration data | CI/service graph domain | Import/reconcile/merge/retire | Reconciliation approval if configured | CMDB schema/mappings | No security admin by default | merge/source precedence
Service Owner | Own service quality | Owned service + related work/SLAs | Service metadata/subscriptions | Selected service approvals | Service config | Cannot bypass change controls | criticality/SLA changes
Integration Admin | Configure connectors | Connector config/logs | Connections/mappings/schedules | Activation if policy grants | Integration catalog | Never view secret values after save | connection/secret-ref changes
AI Admin | Configure AI | AI config/traces/evals by policy | Model routing/use-case config | AI policy if entitled | AI settings | No security-role assignment | model/policy/autonomy changes
Security Admin | Security/compliance | Security config/audit/identity metadata | Policies/security settings | Break-glass approvals | Security config | No business fulfillment unless separate role | role/break-glass/retention/key events
Auditor | Independent review | Read-only audit/reports | No | No | No | No mutation | audit exports/searches
Tenant Admin | Tenant configuration | Tenant data/config except restricted secrets | Users/groups/forms/taxonomy/config | Delegated admin approvals | Tenant settings | No platform-operator data | admin changes
Platform Operator | Operate SaaS | Operational metadata; tenant content only via break-glass | Platform ops | No customer business approvals | Infrastructure/platform | Strict support-access controls | support access/deploy/break-glass

## 05_Tech_Architecture
Technical Architecture Specification
Reference architecture; technologies may change if interfaces and NFRs are preserved.
Layer / Component | Responsibility | Recommended Technology | Interface / Protocol | Data Ownership | Scale Model | HA / Resilience | Security Controls | Observability | Key Notes
Web App | Requester portal, agent workspace, admin console | Next.js/React + TypeScript | HTTPS REST; SSE/WebSocket where needed | No durable business state | CDN + horizontal app scale | Stateless replicas | CSP, secure cookies, CSRF/XSS controls | RUM/web vitals/errors | UI is not sole authorization layer.
API Gateway | Routing, auth, quotas, request/tenant/correlation IDs | Managed gateway/Envoy/Kong-style | HTTPS REST | No durable state | Horizontal | Multi-AZ | WAF, JWT validation, mTLS internal, quotas | RED metrics/traces | Propagate tenant + trace IDs.
Identity | SSO, sessions, SCIM | Enterprise IdP integration or identity service | OIDC/SAML2/SCIM2 | Identity metadata | Horizontal | Multi-AZ | Key rotation/session policy/MFA via IdP | Auth success/fail/anomaly | Minimize stored identity data.
Authorization / Policy | RBAC/ABAC/record/field/action/SoD/AI policy | OPA/Cedar-style or dedicated service | Internal API/SDK | Policy definitions/decisions | Horizontal + cache | Fail closed | Signed policy config/admin audit | Decision latency/denies | One policy model across API/workflow/AI.
Core ITSM Domain | Incident/problem/change/request/KB/SLA/task logic | Python/FastAPI, Java/Kotlin, or TypeScript; modular monolith initially acceptable | REST + domain events | Transactional domain data | Horizontal | Multi-AZ | Tenant scope, validation, authz | RED + domain KPIs | Preserve module boundaries.
Workflow Orchestrator | Long-running workflows, approvals, timers/retries | Temporal/Camunda-style durable engine | Workers/events | Workflow state | Worker pools | Durable/replay | Worker identity/action allowlist | Workflow age/retries/stuck | Prefer mature engine over custom durability.
Rules Engine | Assignment/validation/defaults/business rules | Declarative rules + safe expression DSL | Internal API | Versioned config | Horizontal | Rollback versions | No unsafe arbitrary code | Exec count/duration/error | Trace each execution.
Relational DB | System of record | Managed PostgreSQL-compatible | SQL via service layer | OLTP data | Read replicas/partitioning later | Multi-AZ + PITR | TDE/TLS; RLS defense-in-depth | Locks/slow queries/replication | Tenant key on every tenant-owned table.
Search | Full-text/facets/semantic hybrid | OpenSearch/Elasticsearch-compatible | Search API | Derived index | Shards/replicas | Rebuildable | ACL-aware query/index design | Latency/index freshness | No sensitive post-filter-only design.
Vector/Semantic Index | RAG retrieval | pgvector/managed vector/search vector fields | Internal retrieval | Embeddings + source pointers | Tenant partitions | Rebuildable | Tenant namespaces + ACL metadata | Recall/latency/freshness | Source of truth remains outside vector store.
Object Storage | Attachments/exports/import files | S3/Blob/GCS-compatible | Signed URLs/internal SDK | Binary objects | Elastic | Cross-AZ | Encryption, AV, bucket policy | Access/scan failures | Metadata/auth in DB.
Event Bus | Domain events/integration fan-out | Kafka/PubSub/SNS+SQS/Event Hubs-style | Async events | Event stream | Partitioned | Replication/DLQ | Schema registry/producer identity | Lag/retry/DLQ | At-least-once; idempotent consumers.
Workers | Async imports/exports/notifications/actions | Containerized worker pools | Queues/events | Execution state transient | Autoscale | Retries/DLQ | Scoped identity/egress policy | Queue depth/duration/failure | Separate noisy/high-risk pools.
Notification Service | Email/SMS/chat/web notifications | Provider adapters + templates | Provider API/SMTP/OAuth | Delivery logs | Horizontal | Provider fallback optional | Template escaping/rate limits | Delivery/bounce/retry | Protect internal notes.
Integration Hub | Connectors/transform/checkpoint/retry | Connector SDK + workflow actions | REST/webhook/SFTP optional/OAuth | Connector config/checkpoints | Per-connector workers | Checkpoint/replay | Vault refs/least privilege/egress allowlist | Sync lag/health | Secrets only by reference.
Secret Management | Integration credentials/signing keys | CyberArk/HashiCorp Vault/cloud Key Vault/Secrets Manager | Workload identity/mTLS | Secrets only | Managed HA | HA by provider | No plaintext in DB/log/config | Secret access audit | Support client-owned vault.
AI Model Gateway | Model routing/policy | Provider-neutral gateway with OpenAI/Anthropic/Azure/Google/open-weight adapters | Provider HTTPS/local inference | Prompt/response metadata per policy | Horizontal | Explicit fallback | Redaction/model allowlist/prompt-injection controls | Tokens/cost/latency/safety blocks | No direct business side effects.
Agent Runtime / Tool Gateway | Plan, authorize, invoke typed tools, postcheck | Dedicated agent orchestrator + workflow engine | Internal APIs | AI execution trace | Worker pools | Checkpoint/retry | Typed tool schemas/RBAC/approval/idempotency/vault refs | Task success/tool failures/blocks | Models never receive DB/shell/cloud credentials.
Analytics Store | KPI snapshots/trends/reporting | Read model/warehouse; Postgres initially, ClickHouse later | SQL/report API | Derived facts | Independent scale later | Replicated | Row/column policy | Freshness/query latency | Keep heavy reports off OLTP at scale.
Audit Store | Tamper-resistant audit/AI trace | Append-only store + immutable export/object lock/SIEM | Internal event API | Audit evidence | Time/tenant partitions | Replicated/retained | Restricted write/read roles/integrity | Gap/hash verification | Separate from general app write path.
Observability | Logs/metrics/traces/SLO | OpenTelemetry + Prometheus/Grafana/managed equivalents | OTLP | Operational telemetry | Horizontal | Multi-AZ | Redaction/access control | SLO dashboards/alerts | Correlation across UI→API→workflow→AI.
Deployment Runtime | SaaS/private cloud/customer-hosted | Kubernetes/managed containers + Terraform/OpenTofu | Container/network | Deployment metadata | Horizontal | Multi-AZ; multi-region option | Network policy/workload identity/signed images | Cluster/app telemetry | Environment profiles, not customer forks.

## 06_Data_Model
Canonical Data Model
Logical entities and key relationships. Physical schema may normalize/partition further.
Entity | Purpose | Key Fields | Primary Relationships | Tenant Key | Lifecycle / State | Sensitive Data | Retention Notes | Indexes / Constraints | API Resource
tenant | Customer isolation domain | id,name,region,status,config_profile | owns tenant data | id | active/suspended/closed | Commercial/config | Contract/legal | unique slug | platform-only
user | Identity profile | id,external_id,email,display_name,locale,timezone,status | org,groups,roles,manager | tenant_id | active/inactive | PII | Identity policy | external_id/email | /users
group | Resolver/business group | id,name,type,manager | members,roles,queues,services | tenant_id | active/inactive | Low | Business | name/domain | /groups
task | Base work record | id,number,type,state,priority,summary,assignee/group,timestamps | parent/child,SLA,journal | tenant_id | generic lifecycle | May contain PII | Module policy | number/state/assignment/time | /tasks
incident | Service interruption | task_id,impact,urgency,category,service_id,ci_id,resolution | problem,MIM,changes | tenant_id | new→closed | Support content | Configurable | priority/service/assignment/time | /incidents
major_incident | High-impact coordination | incident_id,commander,comms_lead,impact,declared/restored | services,stakeholders,PIR | tenant_id | candidate→closed | Operational | Longer evidence | declared/service | /major-incidents
problem | Underlying cause | task_id,RCA,workaround,known_error,fix | incidents,changes,KB,CIs | tenant_id | assess→closed | Support content | Configurable | state/service/time | /problems
change_request | Controlled change | task_id,model,risk,schedule,plans | CIs,services,approvals,tasks,incidents | tenant_id | draft→closed | Operational | Long audit | schedule/risk/state | /changes
request | Order container | task_id,requested_for,opened_by,state | request_items | tenant_id | submitted→closed | PII possible | Configurable | requested_for/time | /requests
request_item | Catalog fulfillment item | task_id,request_id,item_version,variables,state | tasks,approvals | tenant_id | pending→closed | Sensitive variables possible | Catalog policy | item/state | /request-items
catalog_item | Orderable service/product | id,version,name,category,eligibility,variable_schema,flow_version | service/workflow | tenant_id | draft/published/retired | Policy metadata | Retain versions | key/version | /catalog-items
knowledge_article | Knowledge | id,number,version,title,body,taxonomy,audience,owner,expiry | source records/feedback | tenant_id | draft→retired | Can be sensitive | Retain versions | fulltext/audience | /knowledge
configuration_item | Managed CI | id,class,name,identifiers,criticality,owner,source,lifecycle | relationships,services,work | tenant_id | planned→retired | Infra metadata | Retain history | identity indexes | /cis
ci_relationship | Service graph edge | parent_ci,child_ci,type,source,confidence,validity | CIs | tenant_id | active/expired | Infra metadata | Retain history | unique active edge | /ci-relationships
service | Business/technical service | id,name,type,owner,criticality,support_group,hours | offerings,CIs,SLAs | tenant_id | active/retired | Business metadata | Long-lived | name/type | /services
sla_definition | SLA policy | id,target_type,conditions,duration,calendar,pause/stop | task_sla | tenant_id | draft/active/retired | Low | Retain versions | active/version | /sla-definitions
task_sla | Running SLA | task_id,definition_version,start,pause,due,breach,elapsed | task | tenant_id | running/paused/completed | Low | Task retention | task/state/due | /task-slas
approval | Decision record | id,target,approver,state,requested/decided,comment | change/request/task | tenant_id | requested→decision | PII possible | Audit retention | target/state/approver | /approvals
journal_entry | Activity item | id,task_id,type,visibility,author,body,timestamp | task | tenant_id | append-only | PII/secrets possible | Record policy | task/time | /activities
attachment | File metadata | id,target,object_key,filename,mime,size,hash,scan_status | any record | tenant_id | uploaded/quarantined/available/deleted | Potential sensitive | Object policy | target/hash | /attachments
workflow_definition | Versioned automation | id,key,version,schema,status,checksum | catalog/change/etc | tenant_id | draft/published/retired | Config | Retain versions | key/version | /workflows
workflow_execution | Durable execution | id,definition_version,target,state,current_step,correlation_id | tasks/approvals/actions | tenant_id | running→complete | Context may be sensitive | Operational retention | target/state/time | /workflow-executions
integration_connection | Connector config | id,type,auth_ref,endpoint,scopes,status | sync jobs/actions | tenant_id | active/disabled | Secret reference only | Config | type/status | /connections
audit_event | Security/admin trace | id,event_type,actor,subject,action,hashes,correlation,time | any | tenant_id | append-only | Security sensitive | Long/immutable | time/type/actor | restricted
ai_execution | AI task trace | id,use_case,model,goal,evidence_refs,tool_calls,policy,cost,outcome | records/approvals | tenant_id | planned→complete/blocked | Prompts may be sensitive | AI policy | use_case/time/model | restricted
notification | Delivery trace | id,event,channel,recipient,template,status,provider_id | source record | tenant_id | queued/sent/failed | Contact data | Operational | status/time/recipient | /notifications
metric_snapshot | Historical KPI fact | metric,dimensions,period,value,definition_version | source events | tenant_id | immutable | Aggregated | Analytics | metric/period/dim | /analytics

## 07_API_Integrations
API & Integration Contract Plan
Minimum integration surface for a credible ITSM ecosystem.
ID | Interface | Direction | Use Case | Auth | Core Contract | Idempotency | Rate / Retry | Security Requirements | Release | Acceptance
API-001 | REST /incidents | Bi-directional | Create/query/update/resolve incident; activities/relationships | OAuth2/OIDC | Versioned OpenAPI; ETag/version concurrency | Idempotency-Key create/actions | Tenant quota + 429 | Object/field ACL, tenant binding, audit | MVP | Contract + negative auth tests
API-002 | REST /requests /catalog-items | Bi-directional | Browse eligible catalog, order, track | OIDC/OAuth2 | Eligibility server-side; typed variables | Order idempotency key | Quota | No crafted-payload eligibility bypass | MVP | Duplicate submit returns same order
API-003 | REST /changes | Bi-directional | DevOps change create/update/evidence | OAuth2 workload identity | Restricted action endpoints | Idempotent actions | Quota | SoD/approval cannot be bypassed | V1 | Pipeline integration test
API-004 | REST /cis | Bi-directional | CMDB import/query/impact | OAuth2 service token | Bulk + source attribution + dry run | Source+external_id | Batch limits | Reconciliation + tenant isolation | V1 | Conflict/reconcile tests
API-005 | Knowledge/Search API | Read/controlled write | Portal/agent search, authoring | OIDC/OAuth2 | ACL-aware results + versions | Write idempotency | Search quotas | No snippet leakage | MVP | ACL leakage suite
API-006 | Webhook subscriptions | Outbound | Domain/SLA/workflow/security events | HMAC + optional mTLS | Versioned CloudEvents-like envelope | event_id | Backoff/DLQ/replay | Signing rotation/allowlist optional | V1 | Replay idempotent
API-007 | Inbound event endpoint | Inbound | Monitoring/AIOps signals | OAuth2/mTLS | source_event_id,severity,resource hints,time,payload ref | source_event_id | Burst control | Validate/quarantine untrusted payload | V2 | Correlation tests
API-008 | Email ingestion | Inbound | Create/update records from mailbox | Provider OAuth/signed pipeline | Thread/message correlation | Message-ID | Retry/dedupe | Sender identity rules + file scan | MVP | Spoof cannot privilege-update
API-009 | Teams/Slack | Bi-directional | Chat support, approvals, notifications | OAuth2 | Bot/actions/deep links | provider event id | Provider retry | Workspace↔tenant binding/min scopes | V1.5 | Cross-tenant token rejected
API-010 | Directory connector | Bi-directional | User/group sync and approved access action | SCIM/OAuth2 | SCIM + typed actions | external id | Checkpoint/retry | Vault, least privilege | V1.5 | Deprovision reconciliation
API-011 | DevOps connectors | Bi-directional | Build/PR/deploy/change evidence | OAuth app/workload identity | Signed webhooks + APIs | provider event id | Provider retry | Repo/project allowlist | V1.5 | Signature/project mapping tests
API-012 | Vault connector | Read by reference | Resolve secret at execution | Workload identity/mTLS | secret_ref only | N/A | Short cache TTL | Never log/return secret; audit access | MVP | Redaction test
API-013 | SIEM export | Outbound | Security/audit streaming | mTLS/OAuth | Normalized events | event_id | Buffered/replay | Redact business content by policy | V1.5 | Loss/replay monitoring
API-014 | Tenant data export | Outbound | Portability/backup | Admin + step-up | Async CSV/JSON/NDJSON + attachment manifest | export job id | Async | Encrypted expiring link + audit | V1 | Core record reconstruction

## 08_AI_Agents
AI & Agentic System Specification
The model proposes; deterministic platform policy authorizes and executes.
Agent / Skill | Trigger | Inputs | Permitted Read Context | Permitted Tools | Autonomy Level | Human Gate | Outputs | Safety / Policy | Evaluation Metrics | Release | Fail-Safe
Incident Triage | New/untriaged incident | Description/requester/channel/service hints | Incident fields,taxonomy,CMDB,known errors,similar incidents | Suggest classification/assignment/link candidates | Recommend only | Agent accepts/overrides | Suggestions + confidence/evidence | ACL-aware retrieval; no sensitive inference | Classification/routing accuracy, override | V1 | Low confidence → default queue
Incident Investigation | Agent request/policy trigger | Incident/activity/diagnostics/service/CI | KB,known errors,related incidents,changes,service graph | Read-only diagnostics/request data/draft plan | Recommend/read-only | Write/action approval | Evidence-backed investigation plan | Tool allowlist,prompt-injection defense | Groundedness,next-step utility,tool correctness | V1.5 | Stop on conflict/inaccessible data
Incident Resolution | Eligible low-risk case | Validated goal/runbook/target identity | Minimum case/runbook context | Typed runbook actions | Bounded autonomous | Risk-based approval | Action result + verification + resolution draft | Pre/postcheck,rollback,idempotency,blast limit | Task success,rollback,unauthorized action | V2 | Failed postcheck → rollback/escalate
Change Plan | Draft change | Description/environment/service/CI/history | Approved templates + prior successful changes + KB | Draft plan only | Recommend | Initiator review | Implementation/test/rollback draft | No invented commands; assumptions labeled | Completeness/edit distance/factuality | V1.5 | Ask questions instead of guessing
Conflict Assessor | Assess/schedule change | Schedule,graph,other changes,freeze | CMDB/calendar/change records | Read-only analysis | Recommend | Change manager | Conflict list + graph/schedule evidence | Deterministic engine authoritative | Seeded conflict recall/explanation | V1.5 | Flag stale/weak graph
Problem/RCA Assistant | RCA | Linked incidents/changes/timeline | Incident cluster,known errors,graph,KB | Hypotheses/evidence requests | Recommend | Problem manager | Hypothesis/evidence matrix | No root-cause certainty without evidence | False certainty/usefulness | V1.5 | Explicit insufficient evidence
Knowledge Drafting | Resolved work | Resolution/RCA/evidence | Authorized source records | Draft article only | Recommend | Publisher | KB draft + tags + citations | PII/secret redaction + audience policy | Citation coverage/edit distance | V1.5 | No auto-publish
Requester Assistant | Portal/chat | Question,identity,own tickets,eligibility | Published KB + own records + eligible catalog | Search,draft incident/request,status | Transactional with confirmation | Confirm submit/high-impact | Answer/order summary/ticket draft | No internal notes; identity binding | Deflection/completion/escalation quality | V1.5 | Human handoff
Shift Handoff | Shift change | Open work/MIMs/risky changes/SLA risk | Team-authorized records | Draft summary | Recommend | User review | Prioritized handoff + links | No cross-team leakage | Critical coverage/false inclusion | V1.5 | Deterministic list fallback
AI Orchestrator | Explicit agentic workflow | Goal,policy,state | Only delegated context | Specialized agents/tools via gateway | Policy-bounded | Dynamic risk tier | Structured plan/status/result | Max steps/cost/time; no privilege inheritance | Task success/escalation/cost/safety | V2 | Hard stop on limit/permission

## 09_Security_GRC
Security, Privacy & Governance Requirements
Security requirements are release gates, not post-launch hardening.
Req ID | Domain | Requirement | Technical Control | Verification | Priority | Release | Owner | Evidence Artifact | Framework Mapping | Notes
SEC-001 | Tenant Isolation | Enforce tenant boundary everywhere | Tenant context + repository enforcement + DB RLS defense-in-depth + tenant-aware cache/search/queue | Cross-tenant automated tests | P0 | MVP | Security | Isolation test report | SOC 2 / ISO 27001 | Never trust tenant ID from body alone
SEC-002 | Authentication | Enterprise SSO/session security | OIDC/SAML, MFA via IdP, short-lived tokens, rotation, secure cookies | SSO/session tests | P0 | MVP | Security | Auth test | NIST concepts / SOC 2 | Step-up for high-risk actions
SEC-003 | Authorization | Least privilege RBAC/ABAC/SoD | Central policy, deny default, field/action scopes | Negative authorization suite | P0 | MVP | Security | Permission matrix | SOC 2 / ISO 27001 | Same policy for API/workflow/AI
SEC-004 | Secrets | No shared plaintext credentials | Vault/workload identity/secrets by reference/rotation | Secret scanning/log review | P0 | MVP | Security | Vault evidence | SOC 2 / ISO 27001 | Never put passwords in tickets/prompts/config
SEC-005 | Encryption | Encrypt transit/rest/backups | TLS1.2+ (prefer 1.3), managed encryption, encrypted backups | Config scan | P0 | MVP | Platform | Encryption evidence | SOC 2 / ISO 27001 | CMK option later
SEC-006 | Audit | Immutable privileged/business/AI audit | Append-only audit, integrity, SIEM export | Completeness sampling | P0 | MVP | Security | Audit evidence | SOC 2 / ISO 27001 | Actor,target,time,correlation,before/after summary
SEC-007 | Logging | No sensitive leakage in logs | Structured logging/redaction/prohibited fields/secret detector | Automated scan | P0 | MVP | Platform | Redaction test | OWASP | Use IDs over record bodies
SEC-008 | Application Security | Common web/API defenses | Schema validation, parameterized DB, XSS/CSRF/SSRF controls, file scan | SAST/DAST/fuzz | P0 | MVP | Security | Security report | OWASP ASVS/API | Connector payloads untrusted
SEC-009 | Rate Limits | Abuse/DoS/cost protection | Per tenant/user/IP/service quotas/concurrency/cost guards | Load/abuse test | P1 | MVP | Platform | Quota config | OWASP API | Separate AI/action quotas
SEC-010 | Privacy | Minimize/classify/retain data | Field classification/masking/retention/export/delete | Privacy review | P0 | V1 | Privacy | Data inventory | GDPR | Legal retention exceptions documented
SEC-011 | Residency | Regional data placement | Region-bound DB/object/search/vector/backup and model routing | Deployment verify | P1 | V1.5 | Platform | Residency design | GDPR/contracts | No cross-region telemetry with content
SEC-012 | Backup/Recovery | Encrypted backup/PITR/restore tests | Managed backups + restore runbooks | Restore test | P0 | MVP | Platform | Recovery report | SOC 2 availability | RPO/RTO in NFR
SEC-013 | Vulnerability Mgmt | Secure SDLC | SCA/SAST/DAST/container scan/SBOM/severity SLAs | CI gate/scan | P0 | MVP | Security | Scan reports | SOC 2/ISO | Block critical exploitable issues
SEC-014 | Supply Chain | Signed immutable builds | Pinned deps, SBOM, signed images/artifacts/provenance | CI verification | P1 | V1 | DevOps | SBOM/signatures | SLSA concepts | No mutable prod tags
SEC-015 | Infrastructure | Runtime/network hardening | Private networking,WAF,network policies,workload identity,non-root,egress control | CSPM/IaC review | P0 | MVP | Platform | IaC evidence | CIS concepts | Customer-hosted must preserve controls
SEC-016 | Privileged Access | JIT/break-glass production access | SSO/MFA/JIT/session audit/support reason | Access review | P0 | MVP | Security | PAM evidence | SOC 2/ISO | No shared admins
SEC-017 | Attachments | Secure file handling | Signed upload,AV/quarantine,MIME controls,DLP hook | Malicious-file tests | P0 | MVP | Security | Attachment report | OWASP | Never execute active upload
SEC-018 | Integration Security | Least-privilege connector identity | OAuth/service principals/scopes/signed webhooks/egress policy | Connector review | P0 | V1 | Security | Connector checklist | SOC 2 | Separate connection per tenant
SEC-019 | AI Security | Prompt injection/data exfil defenses | Instruction/data separation,untrusted labels,ACL retrieval,tool validation,output controls | Adversarial AI tests | P0 | V1 | AI Security | Red-team report | OWASP LLM guidance | Retrieved content cannot redefine policy
SEC-020 | AI Governance | Model/tool/autonomy governance | Model allowlist,data policy,autonomy tier,max steps/cost,human gate,trace | Policy tests | P0 | V1.5 | AI+Security | AI policy evidence | NIST AI RMF concepts | Platform auth overrides agent intent
SEC-021 | AI Privacy | Prompt/response retention/training controls | Provider no-training where available, configurable logging/redaction/residency | Provider/config review | P0 | V1 | Privacy | Provider controls | GDPR/contracts | Tenant can disable external models
SEC-022 | Deletion/Export | Verified portability/purge | Async scoped export + reconciled purge across DB/search/vector/object/cache | Reconciliation test | P1 | V1.5 | Privacy | Deletion/export proof | GDPR | Audit retains lawful minimal metadata
SEC-023 | Incident Response | Security IR and evidence preservation | Security alerts/runbooks/customer notification workflow | Tabletop | P1 | V1 | Security | IR runbook | SOC2/ISO | Link product incident if useful
SEC-024 | BCP/DR | Resilience/DR controls | Multi-AZ,dependency inventory,regional recovery plan | DR exercise | P1 | V1 | Platform | DR report | SOC 2 availability | Multi-region optional by tier
SEC-025 | Change Control | Production deployment governance | PR review, CI gates, approvals, artifact promotion/rollback/audit | Release audit | P0 | MVP | DevOps | Release record | SOC 2 change mgmt | Dogfood change module later
SEC-026 | Sensitive UX | Discourage secrets in tickets | Field masking/classification + user warnings and detectors | UX/security test | P1 | V1 | Privacy | UX evidence | GDPR | Never request passwords
SEC-027 | Pen Test | Independent external pen test | Web/API/auth/tenant/agentic boundaries | Third-party test | P0 | V1 | Security | Pen test report | SOC2 readiness | Close high/critical before GA

## 10_NFR_SLO
Non-Functional Requirements & Service Objectives
Initial engineering targets; commercial SLAs should be defined separately.
NFR ID | Category | Requirement / Target | Scope | Measurement Method | Priority | Release | Degradation Strategy | Test Type | Notes
NFR-001 | Availability | Core API monthly internal SLO ≥99.9% | Core API/web | Valid-request success SLI | P0 | V1 | Safe degraded/read-only modes where possible | Chaos/Uptime | Commercial SLA separate
NFR-002 | Performance | p95 core read ≤500ms; standard mutation ≤800ms excluding async work | Core APIs | Traces/load test | P0 | MVP | Queue async work/disable enrichment | Load | Search/AI separate targets
NFR-003 | Portal Performance | p75 LCP ≤2.5s on representative broadband | Requester portal | RUM/synthetic | P1 | MVP | Defer noncritical widgets | Frontend perf | Use realistic content
NFR-004 | Search | p95 keyword ≤1.5s; semantic ≤2.5s under target load | Search | Telemetry | P1 | V1 | Fallback semantic→keyword | Load/Relevance | Security filters mandatory
NFR-005 | Scalability | Reference SaaS supports ≥1,000 tenants and millions of task records with partition/index strategy | Platform | Capacity test/schema review | P1 | V1.5 | Scale workers/index/read replicas | Capacity | Commercial tier limits later
NFR-006 | Concurrency | Prevent record corruption under concurrent agent/requester updates | Core | Concurrency tests | P0 | V1 | Optimistic conflict UI | Concurrency | No silent last-write-wins for critical fields
NFR-007 | Workflow Durability | No lost workflow/timer state after process/node restart | Workflow | Fault injection | P0 | MVP | Replay durable state | Chaos | Idempotent actions
NFR-008 | RPO | Core transactional data target RPO ≤15 min reference profile | Data | Backup/replication verify | P0 | V1 | PITR restore | DR | Audit may be stronger
NFR-009 | RTO | Regional disaster reference target ≤4h restoration | Platform | DR exercise | P1 | V1 | Restore auth→DB→API→portal→async | DR | Premium lower RTO later
NFR-010 | Accessibility | WCAG 2.2 AA-aligned core requester/agent journeys | Web | Automated + manual | P0 | MVP | Block inaccessible critical feature | Accessibility | Assess embedded third-party UI
NFR-011 | Browser | Current + previous Chrome/Edge/Firefox; current Safari for requester portal | Web | Cross-browser suite | P1 | MVP | Document unsupported | Compatibility | Agent can prioritize Chrome/Edge initially
NFR-012 | API Compatibility | No breaking change inside supported major API; deprecation window documented | Public API | Contract tests | P0 | V1 | Version endpoint/field | Contract | Schema evolution rules
NFR-013 | Event Compatibility | Versioned event schema; additive evolution default | Events | Consumer contract tests | P1 | V1 | Dual publish if breaking migration | Contract | Immutable event_id
NFR-014 | Import | Large imports resumable/checkpointed with row-level error reporting | Migration/CMDB | Scale import test | P1 | V1.5 | Pause/retry/batch | Performance | No single giant transaction
NFR-015 | Export | Async tenant export resumable with integrity manifest | Portability | Large export test | P1 | V1 | Chunked files/job resume | Perf/Security | Expiring secure delivery
NFR-016 | Audit Completeness | 100% privileged/admin/AI tool actions have actor/time/target/context IDs | Audit | Invariant test | P0 | MVP | Fail sensitive action if policy requires audit write | Security | Define availability tradeoff per event
NFR-017 | Observability | All services emit structured logs, metrics and traces with correlation/tenant IDs | Platform | Telemetry coverage | P0 | MVP | Buffer where safe | Operational readiness | Redact sensitive fields
NFR-018 | Localization | All UI strings externalized; backend timestamps UTC | All | Static/timezone tests | P1 | V1 | Fallback language | Functional | No locale-formatted dates as storage
NFR-019 | Maintainability | ADRs, module boundaries, contracts, automated migrations and rollback strategy | Codebase | Architecture review | P0 | MVP | Reject undocumented coupling | Architecture | Modular monolith acceptable
NFR-020 | Testability | Meaningful unit coverage target ≥80% plus integration/contract/E2E for critical flows | Codebase | CI quality gates | P0 | MVP | Block critical regressions | CI | Coverage is not scenario quality
NFR-021 | AI Latency | Interactive AI p95 target ≤8s; longer agentic tasks async with progress | AI | Gateway telemetry | P1 | V1 | Fallback model/non-AI path | Performance | Never block record save on AI
NFR-022 | AI Groundedness | Operational answers cite authorized evidence and meet use-case threshold | AI | Eval harness | P0 | V1 | Refuse/ask when evidence insufficient | AI Evaluation | Use per-skill thresholds
NFR-023 | AI Safety | 0 tolerated successful critical privilege-escalation cases in adversarial release set | AI actions | Red team/eval | P0 | V1.5 | Disable use case/model/tool | Security Eval | Release blocker
NFR-024 | Cost Control | Per-tenant AI/integration quotas, alerts, model routing and safe caching | AI/Integrations | Cost telemetry | P1 | V1.5 | Downgrade/approval at threshold | FinOps | Never cross-user/tenant cache sensitive outputs

## 11_Dev_Workstreams
Development Workstreams & Definition of Done
Sequencing plan without calendar dates; assign dates after staffing/estimation.
Workstream | Sequence | Scope | Primary Deliverables | Depends On | Suggested Team | Entry Gate | Exit / Definition of Done | Release | Risk | Notes
Architecture & Platform | 1 | Repo/module boundaries, ADRs, environments, CI/CD, tenant model, API/telemetry baseline | Reference service + IaC + CI + trace | None | Principal Architect, Platform, DevOps, Security | Product scope approved | Reference transaction works end-to-end with auth/tenant/audit/trace | MVP | High | Freeze contracts, not implementation details
Identity / Authorization / Audit | 2 | SSO, sessions, RBAC/policy, SCIM skeleton, audit model | Auth + policy SDK + audit store | Architecture | Backend + Security | Threat model | Negative auth tests pass; admin/security actions auditable | MVP | Critical | Everything depends on this
Core Task Framework | 3 | Task base, numbering, forms, activity, attachments, assignment, relationships | Shared task domain/UI | Identity | Backend + Frontend | Schema baseline | Create/update/query with permissions/audit/attachments/activity | MVP | High | Avoid premature over-generalization
Workflow / Rules / Scheduler | 4 | Durable workflows, timers, rules, scheduled jobs, retry/idempotency | Workflow runtime + rules + scheduler | Core platform | Platform | Event model ready | Approval/timer flow survives restart/failure | MVP | Critical | Prefer mature engine
Incident + SLA | 5 | Incident lifecycle/routing/priority/SLA/queue/resolution/notifications | Production incident flow | Core task/workflow | Backend + Frontend + QA | Task stable | Portal/email/API incident resolves with SLA/audit | MVP | High | First dogfood module
Portal + Request + Catalog + KB | 6 | Self-service/catalog/order/approvals/fulfillment/knowledge | Employee portal | Workflow/search | Frontend + Backend + UX | Incident/auth stable | Self-solve/order journeys pass incl accessibility | MVP | High
CMDB Foundation | 7 | CI classes/import/basic relationships/service model | CI/service context | Import platform | Backend + Data | Tenant/schema stable | Work references valid CIs/services; dry-run import works | MVP/V1 | High | Basic MVP; graph health V1
Problem Management | 8 | Problem/RCA/known error/remediation | Problem module | Incident/KB/CMDB | Backend + Frontend | Incident stable | Problem links incidents, publishes known error, drives fix | V1 | Medium
Change Management | 9 | Models/risk/approvals/conflicts/calendar/CAB/implementation/review | Change module | CMDB graph/workflow | Backend + Frontend + QA | CMDB usable | Normal/standard/emergency E2E pass | V1 | Critical | Validate with change SME
Major Incident + On-call | 10 | MIM workspace/comms/escalation/rotations/PIR | Major incident ops | Incident/notifications | Backend + Frontend + Integrations | Incident operational | Game day executes war room/comms/on-call/PIR | V1 | High
Agent Workspace | 11 | Unified workspace/queues/context/quick actions/collab | Resolver experience | Core modules | Frontend + UX | Modules usable | Target agent journeys meet UX/perf criteria | V1 | Medium | Develop alongside modules
Analytics | 12 | KPI library/dashboards/snapshots/CSAT | Operational reporting | Events/lifecycle stable | Data + Frontend | Event semantics stable | Metrics reconcile and history stays stable | V1 | Medium
AI Foundation | 13 | Model gateway/RAG/eval/policy/trace/copilot | Governed AI layer | Search/policy/audit | AI + Backend + Security | Permission-aware retrieval ready | Triage/summary pass quality/security eval | V1 | Critical | No AI without eval/trace
Integrations & Migration | 14 | Public APIs/webhooks/email/directory/collab/DevOps/import | Ecosystem readiness | Core modules | Integration Eng | Contracts stable | Representative connectors pass retry/security tests | V1/V1.5 | High | Connector certification checklist
Workflow Builder / Admin | 15 | Visual builder/config transport/delegated admin | Config-first implementation | Workflow stable | Frontend + Platform | Primitives stable | Admin builds/promotes supported flow without code | V1.5 | High | No unsafe arbitrary code
Agentic Automation | 16 | Tool gateway/bounded actions/HITL/handoff/autonomy eval | Governed autonomous workflows | AI/workflow/vault | AI + Security + Automation | Safety gates established | Low-risk workflows pass pre/postcheck/rollback/no escalation | V1.5/V2 | Critical | Tier autonomy by risk
Scale / DR / Enterprise | 17 | Performance/partition/private cloud/residency/DR/SIEM | Enterprise hardening | Core complete | Platform + Security + QA | Functional stable | Load/DR/security/pen-test gates pass | V1.5 | Critical
GA Readiness | 18 | Docs/implementation/API/upgrade/support/security pack | Launch package | All | Product + Eng + QA + Security | All release gates | No critical blockers; rollback/support/security evidence ready | Per release | High

## 12_Test_Acceptance
Testing & Acceptance Strategy
Critical-path test matrix and release gates.
Test Area | Scope | Example Scenarios | Automation Level | Environment | Data Strategy | Entry Criteria | Pass Criteria | Blocking Severity | Owner | Release Gate
Unit | Domain rules/validators/calculations | Priority, SLA math, transitions, risk factors | High | CI | Synthetic | Code complete | Critical tests pass; meaningful coverage met | Critical/High | Developers | Every merge
API Contract | Schemas/actions/versioning | Create/update/query, ETag conflict, invalid payload | High | CI/Test | Synthetic | OpenAPI defined | Consumer/provider contracts green | High | Backend QA | Every release
Authorization | Tenant/RBAC/field/action/SoD | Cross-tenant ID, hidden field, approval bypass | High | Test/Staging | Adversarial tenants | Policy stable | 0 unauthorized successes | Critical | Security QA | Every release
Workflow Durability | Retry/timer/human wait | Worker crash, duplicate event, timeout | High | Test | Synthetic | Workflow integrated | No lost/duplicate side effect | Critical | Platform QA | MVP+
Incident E2E | Intake→routing→SLA→resolution | Portal/email/API, pending, reopen, duplicate | High | Staging | Synthetic personas | Feature complete | P0/P1 journeys pass | Critical/High | QA | MVP
Request/Catalog E2E | Eligibility→approval→fulfillment | Ineligible user, parallel approval, cancel, integration fail | High | Staging | Synthetic org | Catalog ready | No policy bypass; correct state | Critical/High | QA | MVP
Change E2E | Normal/standard/emergency | Risk, conflict, freeze, CAB, rollback | High | Staging | Seeded CMDB/calendar | Change complete | Expected path/evidence exact | Critical | QA + Change SME | V1
CMDB Reconciliation | Identity/source/merge | Duplicate servers/conflicting source/stale CI | High | Test | Generated | Rules set | No destructive merge; conflict visible | High | Data QA | V1
Search Security/Relevance | Keyword/semantic/ACL | Restricted KB, similar incident, typo | High | Staging | Restricted seeded content | Index ready | 0 leakage + relevance target | Critical | QA + AI | V1
AI Quality | Golden skill datasets | Triage/summarize/plan/answer | High | Eval | Versioned gold set | Skill frozen | Thresholds ≥ baseline | High | AI QA | V1+
AI Security | Prompt/tool/privilege abuse | Malicious KB/ticket/tool params/cross-tenant | High | Eval/Staging | Adversarial corpus | Tool gateway ready | 0 critical exploit successes | Critical | AI Security | V1+
Agentic Action | Precheck/execute/postcheck/rollback | Password/group/runbook mocks/failure compensation | High | Sandbox staging | Mock integrations | Policy+tool ready | Correct side effect once; rollback on failed postcheck | Critical | AI/Automation QA | V1.5/V2
Performance | API/search/workflow/import | Concurrent users,event bursts,large tenant | High | Perf | Scale data | Stable build | NFR targets with headroom | High | Performance Eng | V1+
Resilience/Chaos | Dependency failures | DB failover, queue delay, search/model/webhook outage | Med/High | Staging/Perf | Synthetic | Observability ready | Safe degradation/recovery without corruption | High | SRE | V1+
DR/Restore | Backup/regional failure | Restore DB/object/rebuild search and verify | Medium | DR | Backups | Runbook ready | RPO/RTO/integrity pass | Critical | SRE/Security | V1
Accessibility | Core web journeys | Keyboard,screen reader,focus,contrast,errors | Mixed | Staging | Representative | UI stable | Core WCAG criteria pass | High | UX QA | MVP+
Pen Test | Web/API/auth/tenant/AI boundaries | Independent exploit testing | Manual | Pre-prod | Seeded non-prod | Feature freeze | High/critical remediated | Critical | Security | GA
Upgrade/Migration | Schema/config upgrades | Previous version→new, rollback, config transport | High | Staging | Prior snapshot | Scripts ready | No data loss; limits documented | Critical/High | Release Eng | V1+

## 13_Risks_Dependencies
Product Risks, Dependencies & Mitigations
Track architecture/product risks from day one.
Risk ID | Risk / Dependency | Impact | Likelihood | Area | Mitigation | Early Warning | Owner | Release Exposure | Status
R-001 | Trying to match ServiceNow breadth in first release | Critical | High | Scope | Native core ITSM; connector/later boundary for adjacent domains | Backlog growth without customer evidence | Product | All | Open
R-002 | Over-generalized platform abstractions delay usable modules | High | Medium | Architecture | Validate abstractions with incident/request/change before platformizing | Framework work without E2E flow | Architecture | MVP | Open
R-003 | Tenant isolation gaps in search/cache/AI | Critical | Medium | Security | Central policy + tenant-aware keys/indexes + adversarial tests | Cross-tenant IDs in telemetry/results | Security | MVP+ | Open
R-004 | Weak workflow durability/idempotency | Critical | Medium | Platform | Use mature engine; fault injection | Duplicate/lost actions | Platform | MVP | Open
R-005 | Poor CMDB data quality harms risk/impact/AI | High | High | Data/AI | Health metrics, source attribution, confidence and stale-data warnings | Low CI completeness | CMDB | V1+ | Open
R-006 | AI presented as authoritative fact | High | Medium | AI | Citations, confidence, human gates, evals | High override/false certainty | AI | V1+ | Open
R-007 | Agent tools become privileged bypass | Critical | Medium | AI Security | Typed tool gateway, RBAC/SoD, approvals, pre/postcheck, vault refs | Tool call without policy record | Security | V1.5+ | Open
R-008 | Customer custom code creates upgrade forks | High | High | Product | Config-first + stable extension SDK | Customer-specific branches | Architecture | V1+ | Open
R-009 | SLA calculation defects | High | Medium | Domain | Deterministic engine + DST/holiday/pause tests | Manual SLA disputes | QA | MVP | Open
R-010 | Email/chat identity spoofing | Critical | Medium | Security | Strong correlation, limited unauthenticated actions, OAuth channels | Unknown sender updates | Security | MVP+ | Open
R-011 | Reporting load harms OLTP | Medium | Medium | Performance | Metric snapshots/read model/warehouse later | Slow DB during dashboards | Data | V1 | Open
R-012 | Private-cloud variants create forks | High | Medium | Deployment | Single codebase + environment profiles + conformance tests | Customer-specific deployment code | Platform | V1.5 | Open

## 14_Release_Plan
Release Scope & Gates
Relative increments only; no calendar dates assigned.
Release | Product Outcome | Must-Have Scope | AI Capability | Security / Enterprise Gate | Performance / Reliability Gate | User Acceptance Gate | Documentation Gate | Do Not Include Yet | Go/No-Go Owner
MVP | Pilot-ready service desk | Tenant/org/SSO/RBAC/audit; task; incident; SLA; request/catalog; knowledge; portal; email; attachments; basic CI import; workflow | Assistive AI only behind flags | Tenant isolation, SAST/SCA/DAST baseline, vault, encrypted backups | Core API/workflow + restore gate | Incident/request E2E + accessibility | Admin setup, API basics, runbooks | Deep problem/change/MIM, autonomous actions | Product + Eng + Security
V1 | Production-grade full ITSM | Problem, change, MIM, on-call, CMDB graph/health, service model, unified workspace, analytics, SCIM, webhooks | Triage/copilot/RAG/change-plan with eval+trace | Pen test, AI security eval, DR, privacy controls | Load/concurrency/SLO/DR | Service manager/change/problem/MIM UAT | Implementation guide, API docs, security overview | Full AIOps, endpoint mgmt, advanced SAM/HAM | Product + Eng + Security + QA
V1.5 | Enterprise configurable platform | Visual workflow builder, connector framework, migration, config transport, private-cloud/residency | Policy-bounded low-risk agentic actions + optional GMH adapter | Regional controls, PAM/access review, autonomy gate | Scale/import tests | Enterprise pilot validates config-first delivery | Connector/migration/private-cloud guides | Broad multi-agent autonomy/unsafe custom code | Steering Group
V2 | Autonomous service operations foundation | Monitoring/event connectors, proactive candidates, expanded service ops, agentic fulfillment/handoff | Bounded multi-agent orchestration/remediation | Continuous AI red-team and autonomy tier certification | Burst/action orchestration resilience | Operational game days | Agent/runbook governance guide | Unlimited autonomy/direct model credentials | Steering Group + Security

## 15_Benchmark_Sources
Benchmark & Reference Sources
Market references only; do not reproduce proprietary code, UI, or protected content.
Source | What It Informed | URL | Checked | Use | Notes
ServiceNow ITSM | Core scope and AI/self-service direction | https://www.servicenow.com/products/itsm.html | 2026-08-31 | Benchmark | Official product overview
Incident Management | Major incident, routing, omnichannel, on-call/workspace expectations | https://www.servicenow.com/in/products/incident-management.html | 2026-08-31 | Benchmark | Official product page
Problem Management | RCA, known errors, remediation | https://www.servicenow.com/products/problem-management.html | 2026-08-31 | Benchmark | Official product page
Change Management | Risk, CAB, models, DevOps alignment | https://www.servicenow.com/products/change-management.html | 2026-08-31 | Benchmark | Official product page
Request Management | Self-service, approvals, workflow/status | https://www.servicenow.com/products/request-management.html | 2026-08-31 | Benchmark | Official product page
Service Catalog | Catalog builder and request workflows | https://www.servicenow.com/products/it-service-automation-applications/service-catalog.html | 2026-08-31 | Benchmark | Official product page
CMDB Docs | CI/service relationships, reconciliation and data quality | https://www.servicenow.com/docs/r/servicenow-platform/configuration-management-database-cmdb/manage-cmdb.html | 2026-08-31 | Benchmark | Official docs
Service Operations Workspace | Unified agent/service operations experience | https://www.servicenow.com/products/service-operations-workspace.html | 2026-08-31 | Benchmark | Official product page
Agentic AI for ITSM | Triage, investigation, change planning/conflict, PIR use cases | https://www.servicenow.com/docs/r/it-service-management/now-assist-for-it-service-management-itsm/now-assist-itsm-ai-agents-use-cases.html | 2026-08-31 | Benchmark | Our governance/autonomy model is independent